## Project List
Project Id | Project Name | Project Owner | Business User | Criticality | Entity Type | Budget($) | Start Date | Projected End Date | End Date | Status
PMO-01 | Voice recognition | Mathew Joshep | Sophie Turner | High | External | 23000000 | 2020-01-01 | 2020-07-01 | 2020-07-15 | Completed
PMO-02 | Image tracker | Brian Adrian | Arnold Dotty | High | External | 30000000 | 2020-02-15 | 2020-09-25 | 2020-09-03 | Completed
PMO-03 | Vaccine manager | Mathew Joshep | Allen Parker | High | Internal | 25000000 | 2020-01-10 | 2020-12-10 | 2021-01-02 | Completed
PMO-04 | Online health checker | Brian Adrian | Allen Parker | Medium | External | 10000000 | 2020-03-25 | 2020-05-04 | 2020-04-24 | Completed
PMO-05 | Online doctor admin panel | Jessica Adams | Arnold Dotty | Medium | Internal | 5000000 | 2020-02-15 | 2020-07-30 |  | Inprogress
PMO-06 | Electronic store manager | Jessica Adams | Susane Grace | Low | Internal | 500000 | 2020-01-26 | 2020-10-26 |  | Inprogress
PMO-07 | Online drug store | George Anthony | Susane Grace | Low | External | 200000 | 2020-04-28 | 2020-08-12 |  | Inprogress
PMO-08 | Analytical Store | George Anthony | Katie Perry | Low | External | 100000 | 2020-06-10 | 2020-09-10 |  | TBD

## Project Task
Project Id | Task Name | Start Date | End Date | Developer
PMO-01 | Task 1 | 2020-01-02 | 2020-01-04 | Allen
PMO-01 | Task 2 | 2020-01-05 | 2020-01-08 | Allen
PMO-01 | Task 3 | 2020-01-09 | 2020-01-12 | Allen
PMO-02 | Task 1 | 2020-02-17 | 2020-02-19 | Mac
PMO-02 | Task 2 | 2020-02-20 | 2020-03-10 | Mac
PMO-02 | Task 3 | 2020-03-11 | 2020-03-18 | Mac
PMO-02 | Task 4 | 2020-03-19 | 2020-03-22 | Mac
PMO-03 | Task 1 | 2020-01-12 | 2020-01-18 | David
PMO-03 | Task 2 | 2020-01-19 | 2020-01-27 | David
PMO-03 | Task 3 | 2020-01-29 | 2020-02-10 | David
PMO-04 | Task 1 | 2020-03-26 | 2020-04-02 | Ahmad
PMO-04 | Task 2 | 2020-04-03 | 2020-04-07 | Ahmad
PMO-04 | Task 3 | 2020-04-08 | 2020-04-16 | Ahmad
PMO-04 | Task 4 | 2020-04-17 | 2020-04-27 | Ahmad
PMO-05 | Task 1 | 2020-02-16 | 2020-02-19 | Nina
PMO-05 | Task 2 | 2020-02-20 | 2020-02-22 | Nina
PMO-05 | Task 3 | 2020-02-23 | 2020-03-01 | Nina
PMO-06 | Task 1 | 2020-01-27 | 2020-01-30 | Eric
PMO-06 | Task 2 | 2020-02-01 | 2020-02-15 | Eric
PMO-07 | Task 1 | 2020-04-29 | 2020-05-04 | Joseph
PMO-07 | Task 2 | 2020-05-05 | 2020-05-18 | Joseph
PMO-08 | Task 1 | 2020-06-12 | 2020-06-15 | Helen
PMO-08 | Task 2 | 2020-06-16 | 2020-06-19 | Helen
PMO-08 | Task 3 | 2020-06-20 | 2020-06-28 | Helen

## Project Team Lead
Project Id | Project Name | Team Lead
PMO-01 | Voice recognition | Alex John
PMO-02 | Image tracker | Nina Gurrero
PMO-03 | Vaccine manager | Jessica Glad
PMO-04 | Online health checker | Clan Tiguan
PMO-05 | Online doctor admin panel | Alex John
PMO-06 | Electronic store manager | Wendy Bose
PMO-07 | Online drug store | Naina Singh
PMO-08 | Analytical Store | Kathy Simpson

## Project Details
Project Id | Project Name | Internal Integration | External Integration | Integration Type
PMO-01 | Voice recognition | Watson,Google Page,Google Analytics,SSO | UMC Integration, KMS Integration | Two way
PMO-02 | Image tracker | SSO,Google Page | UMC Integration, KMS Integration | One way
PMO-03 | Vaccine manager | SSO,Location Finder | UMC Integration, KMS Integration | Two way
PMO-04 | Online health checker | IBM Rhapsody,Active Directory | UMC Integration, KMS Integration, PMK Integration | Two way
PMO-05 | Online doctor admin panel | IBM Rhapsody,Active Directory | HCP Integration | One way
PMO-06 | Electronic store manager | SSO,IBM Rhapsody | Cloudera Integration,CCP Integration | One way
PMO-07 | Online drug store | Google Sheet | CCA,CCP | Two way
PMO-08 | Analytical Store | Google Analytics | CCK,CSS | Two way

## User Stats
Project Id | Project Name | Total Internal Users | Total External Users
PMO-01 | Voice recognition | 15000 | 34000
PMO-02 | Image tracker | 20000 | 90000
PMO-03 | Vaccine manager | 600 | 1200
PMO-04 | Online health checker | 600 | 1223
PMO-05 | Online doctor admin panel | 4000 | 9833
PMO-06 | Electronic store manager | 800 | 1891
PMO-07 | Online drug store | 300 | 900
PMO-08 | Analytical Store | 50 | 120

## Vendors
Project Id | Project Name | Vendors
PMO-01 | Voice recognition | IBM,MICROSOFT
PMO-02 | Image tracker | INFOSYS
PMO-03 | Vaccine manager | IBM,MICROSOFT
PMO-04 | Online health checker | INFOSYS,HCL
PMO-05 | Online doctor admin panel | GOOGLE,CLOUDERA
PMO-06 | Electronic store manager | GOOGLE,CLOUDERA
PMO-07 | Online drug store | HCL,GOOGLE
PMO-08 | Analytical Store | GCP

## Ratings
Project Id | Project Name | Rating
PMO-01 | Voice recognition | 8
PMO-02 | Image tracker | 9
PMO-03 | Vaccine manager | 6
PMO-04 | Online health checker | 7
PMO-05 | Online doctor admin panel | 6
PMO-06 | Electronic store manager | 7
PMO-07 | Online drug store | 8
PMO-08 | Analytical Store | 9